## Sheet 1
[17 empty] | Rev. | Date | By | Chk'd | App'd | Description
|  |  |  | Document No.: | 008364-003-70-70.02 |  |  | Legend: | [8 empty] | 0 | 2012-11-15 | TD | TD | MB | Initial Issue
|  |  |  | Project No.: | 008364-003 |  |  | Yellow | Change from Previous Report | [7 empty] | 1 | 2013-01-23 | TD | TD | MB | Added column for Final Vendor Data Received
|  |  |  | Project Name: | Howard Energy Reveille BOP |  |  | Green | Shipped
|  |  |  | Client: | Howard Energy |  |  | Orange | Received
PURCHASE ORDER (PO) EXPEDITING LOG
RFQ Ref. No. | PO No. | EXP | Rev. No. | PO Issue Date | Supplier | Contact Information | Equipment Description | Supplier Sch. Rec'd | Date Dwgs Rec'd | Date Dwgs Approved | Fab. Start Date | Est. Hydrotest | Est. FAT / Final Inspection | PO Ship Date | Forecasted Ship Date | Actual Ship Date | Pick Up Point | Transit Time If Required (Days) | MOT Air / Ocean / Truck | Date Delivered to End Location | Delivery Location | Final Vendor Data Received (Y/N) & Date | Comments
C001 | 008364-003-PO-C001 | LC | 0 | 2013-07-02 | SIS | Michael Rasch | RESIDUE COMPRESSION, INST. AIR COMPRESSOR BUILDINGS & GAS CHROMATOGRAPH SHED | 8-Aug-13 (initial) | 2013-07-17 | 2013-07-23 | 2013-08-05 | N/A | N/A | 20 Nov 2013 (Completion) | 10/28 thru 11/07/2013 |  | Houston, TX |  | Truck |  | Jobsite Freer, TX | 2013-11-07 | 01/21: Completion of all site work verified. 01/03: Still expediting completion of site work. 12/23: Expediting SIS for confirmation of site work completion. 11/25: SIS confirms all matls delivered to site except a framed opening with trim & flashing. 11/07: Final Data Books received. 10/29: SIS advises crane will deliver on 11/7 & will be the last shipment. 10/28: Deliveries to site started today. 10/24: SIS to start deliveries to site on 10/28. Final to be 11/4. 10/07: SIS requested to delay start of deliveries until 10/28. 10/4: SIS forecasting 10/21 delivery. 9/25: CO 2 issued adding a Gas Chromatograph Shed. 8/23: Still on schedule. May improve slightly. 8/22: Expediting status update from SIS.
|  |  | 1 | 2013-07-31 |  |  | Modify Cable Tray Support System.
|  |  | 2 | 2013-09-25 |  |  | Add Gas Chromatograph Shed
E001 | 008364-003-PO-E001 (SO# 13-617) | LC | 0 | 2013-04-11 | Moore Control Systems | R. Wesley Fraley 281-392-7747 x310 wfraley@moore-control.com | MCC BUILDING Tag: LV-MCC/CRTL Building Tag: MCC-001 Tag: MCC-002 Tag: UPS-001 | 20-Aug-20113 2-Aug-2013 24-Jul-2013 12-Jul-2013 30-May-2013 | 24-Jul-2013 14-Jun-2013 30-May-2013 8-May-2013 | 24-Jun-2013 10-Jun-2013 14-May-2013 | 2013-07-26 | N/A | 24 - 25 Sep 2013 | 15 - 29 Aug 2013 | 2013-10-02 | 2013-10-02 | Katy, TX | 2 | Truck | 2013-10-03 | Jobsite Freer, TX | 2013-11-04 | 11/22: All major repairs complete. 11/07: Updated report received. Est completion is still 11/22. 10/25: Updated report received. Est completion is still 11/22. 10/15: MCSI status report issued on repairs. Est completion of repairs is 11/22. 10/11: Audubon assisting MCSI coordinate VFD repair with Reynolds.
E004 | 008364-003-PO-E004 (SO# R1USH00436) | LC | 0 | 2013-03-19 | Reynolds Co. | Mike Novoa 713-353-2400 mnovoa@ra.rockwell.com | VFD Tag: VFD-COMN-NGL-PL-PUMPS |  | 17-May-2013 3-May-2013 | 4-Jun-2013 14-May-2013 |  |  | 2013-07-11 | 2013-06-10 | 2013-07-22 | 2013-07-29 | Houston, TX | 0.5 | Truck | 2013-07-29 | Moore Control Katy, TX | 2013-09-05 | 9/05: Final Data received via email. 8/28: Expediting Final Data Books. 7/31: Received POD at MCSI. 7/24: Released to ship to MCSI. 7/12: Still scheduled to ship wk of 7/22 to MCSI. 7/11: FAT held at shop. 7/01: Still on hold.
|  |  | 1 | 2013-04-09 |  |  | Filter (1 Ea)
E004A | 008364-003-PO-E004A (SO# 4823525-00) | LC | 0 | 2013-04-09 | Reynolds Co. | Renee Russell-Head 713-426-8400 (C: 281-723-5655) rnrussell@reynco.com | VFD Tag: VFD-COMN-PUMP-STATION (with Filter) |  | 2013-05-17 | 2013-06-04 |  |  | 2013-07-11 | 2013-07-05 | 2013-07-22 | 2013-07-29 | Houston, TX | 0.5 | Truck | 2013-07-29 | Moore Control Katy, TX | 2013-09-05 | 9/05: Final Data received via email. 8/28: Expediting final data books. 7/31: Received POD at MCSI. 7/24: Released to ship to MCSI. 7/12: Still scheduled to ship wk of 7/22 to MCSI.
G001 | 008364-003-PO-G001 (HVM1304309/10/11/12) | LC | 0 | 2013-04-05 | Houston Vessel MFG | Roy Kuhn 713-973-5200 281-380-7637 (C) rkuhn@houstonvessel.com | VESSELS & DRUMS Tag: V-411 Tag: V-412 | 7-Aug-2013 2-Aug-2013 11-Jul-2013 25-Jun-2013 16-May-2013 22-Apr-2013 | 25-Jun-2013 23-May-2013 22-Apr-2013 19-Apr-2013 | 17-Jul-2013 5-Jun-2013 3-May-2013 2-May-2013 | 2013-06-24 | V-411: 16 Aug V-412: 15 Aug V-413: 12 Sep V-414: 12 Aug | V-411: TBA V-412: TBA V-413:18-Sep V-414: 19-Aug | 12 - 26 Jul 2013 | V-411: TBA V-412: TBA V-413: 23-sep V-414: 19-Aug |  | Houston, TX | 1 | Truck | 2013-09-25 | Jobsite Freer, TX | 2013-10-15 | 10/15: Final Data Books/CDs received. 9/30: Expediting final data books. 9/25: All vessels received at site. 9/25: V-411 & 412 released to ship. 9/23: V-413 arrival delayed to 9/24. 9/18: V-413 released to ship. Will load on 9/20 & arrive @site on 9/23. 9/16: NCR issued for V-411/412 due to paint issues. 9/11: V-411/412 final insp slipped to 9/16 due to weather. 9/09: V-414 shipped to site.
[7 empty] | Tag: V-414 | [8 empty] | 2013-09-09 |  | 1 |  | 2013-09-10
[7 empty] | Tag: V-413 | [8 empty] | 2013-09-23 |  | 1 |  | 2013-09-23
G001A | 008364-003-PO-G001A | LC | 0 | 2013-03-28 | Diverse Energy Systems (DES) | April White 713-358-7000 awhite@des-co.com | STORAGE TANK Tag: V-415 |  | 15-May-2013 9-Apr-2013 | 20-May-2013 18-Apr-2013 | Already Built | N/A | 2013-05-18 | 9 May - 23 May 2013 | 2013-09-09 | 2013-09-11 | McGregor, TX | 2 | Truck | 2013-09-13 | Jobsite Freer, TX | 2013-09-24 | 9/24: Final data book received. 9/23: Vendor to send final data this week. 9/19: Expediting final data. 9/16: Site confirmed receipt on 9/13. 9/11: Tank moving today to site.
G002 | 008364-003-PO-G002 (SO# 13-050223) | LC | 0 | 2013-05-16 | McGraw Equipment | Nate Sneed 281-391-8810 nate.sneed@mcgrawequipment.net | PUMPS Tag: P-607/617/608/609/610/612/613/614/615A/615B | 2013-06-10 | 14-Jun-2013 24-May-2013 | 2013-06-05 | 2013-07-14 | N/A | 2013-08-09 | 9 May - 23 May 2013 | Wk of 12 Aug | 2013-08-15 | Katy, TX | 4 | Truck | 2013-08-19 | Jobsite Freer, TX | 2013-08-29 | 8/29: Final Data received. 8/19: Site receipt confirmed. 8/15: order released to ship. 8/08: Final inspection scheduled 8/09. 8/02: Pumps in-house. Need FRL's & Solenoids piped up. Inspection to follow.
G003 | 008364-003-PO-G003 | LC | 0 | 2013-03-08 | Air Mac | Jim Keller 214-879-1010 jkeller@airmac.com | AIR COMPRESSORS Tag: C-102 A/B, V-417 |  | 10-Jul-2013 22-Apr-2013 2-Apr-2013 | 25 & 18 Apr-13 | 2013-06-14 | N/A | 2013-07-26 | 26 Jul - 23 Aug-2013 | 2013-07-30 | 2013-07-30 | Dallas, TX | 1 | Truck | 2013-07-31 | Jobsite Freer, TX | 2013-08-26 | 8/26: Final Data Books received. 8/19: Expediting final data books. 7/31: Site confirmed receopt. 7/30: Order complete & released to ship. ETA at site on 7/31. 7/23: Inspection rescheduled for 7/26. Ship date still 7/30. 7/19: IAC failed inspection due to defective drive out-put terminal. 7/10: Expedited GA Dwg for V-417 Starting Air Bottle.
|  |  | 1 | 2013-05-29 |  |  | Add 1 Air Receiver
G004 | 008364-003-PO-G004 | TD / LC | 0 | 2013-04-11 | Enterflex Energy Systems | Arun Reddy 281-855-5105 areddy@enerflex.com | VRU Tag: C-103 | 19-Aug-2013 15-Jul-2013 04-Jun-2013 14-May-2013 26-Apr-2013 | 26-Jul-2013 14-May-2013 31-May-2013 4-Jun-2013 | 20-Jun-2013 11-Jun-2013 23-May-2013 | 2013-08-20 | TBA | 2013-09-26 | 9 - 24 Sep 2013 | 20 or 23 Sep-2013 | 2013-09-25 | Houston, TX | 1 | Truck | 2013-09-26 | Jobsite Freer, TX | 2013-10-18 | 10/18: Final data books & CD's received. 10/11: Still expediting final data books. 10/02: Expediting final data books. 9/25: VRU enroute to site. ETA 9/26. 9/20: Released to ship. 9/19: Supplier says he's ready to ship. Awaiting IRC. 9/12: Still scheduled to be completed on 9/26. 9/11: Expedting status update. 9/5: Completeion delayed to 9/26 due to internal shop issues. 9/3: Received the first inspection report today. No major issues or concers at this time.
G005 | 008364-003-PO-G005 | LC | 0 | 2013-03-08 | Peco-Facet | Ron Brown 281-469-3200 x603 ronbro@pecofacet.com | RESIDUE GAS FILTER Tag: F-454 | 18-Jun-2013 10-May-2013 | 28-May-2013 2-May-2013 29-Apr-2013 | 11-Jun-2013 9-May-2013 (QC Docs) | 2013-07-25 | 2013-08-06 | 2013-09-18 | 2013-09-19 | 2013-09-19 | 2013-08-23 | Mineral Wells, TX | 3 | Truck | 2013-08-26 | Jobsite Freer, TX | 2013-09-26 | 9/26: Final data books received. 9/23: Expediting status of final data books. 9/11: Supplier forecasting 9/20 for final data books. 9/10: Still expediting final data books. 9/03: Expediting final data books. 8/26: Site confirmed receipt. 8/23: Released to ship.
|  |  | 1 | 2013-04-11
G006 | 008364-003-PO-G006 (SO# 13-0260) | LC | 0 | 2013-03-08 | Flare Industries | Ryan Spinden 512-836-9473 rspinden@flareindustries.com | SONIC FLARE STACK Tag: FS-800 | 18-Jun-2013 10-May-2013 | 6-Jun-2013 30-Apr-2013 11-Apr-2013 10-Apr-2013 5-Apr-2013 25-Mar-2013 | 9-May-2013 25-Apr-2013 18-Apr-2013 11-Apr-2013 3-Apr-2013 | 2013-05-02 | N/A | 2013-08-08 | 2013-07-26 | 2013-08-22 | 27 & 29 Aug-13 | Austin, TX - & - Houston, TX | 2 | Truck | 2013-08-30 | Jobsite Freer, TX | 2013-10-01 | 10/01: Final data books received. 9/11: Final data to be submitted end of Sep. 9/10: Expediting final data. 8/30: Site confirmed receipt. 8/29: Houston portion of order released to ship. 8/27: Austin portion of order released to ship. 8/20: Supplier reports ship date slippage to wk of 8/26 due to fit up problems. 8/01: Supplier now reporting 8/22 ship date. FAT scheduled for 8/08. 7/12: Updated Prod. Schedule received. Ship date is now 8/08/13. 6/18: Updated Prod. Schedule received. 6/06: Revised GA Dwg & IFC P&ID received at Audubon
G007 | 008364-003-PO-G007 | LC | 0 | 2013-04-09 | Service Welding & Machine | Carl Greer 502-585-4295 cgreer@service-welding.com | TANKS Tag: TK-801, 802 | 19-Jun-2013 18-Apr-2013 (Prelim) | 3-May-2013 26-Apr-2013 18-Apr-2013 16-Apr-2013 | 17-Jun-2013 20-May-2013 30-Apr-2013 25-Apr-2013 | 8 Jul-13 (Week of) | 12 -Aug-2013 (Week of) | 2013-08-14 | 28 Jun - 25 Jul 2013 | 19 Aug 2013 (Week of) | 2013-08-22 | Louisville, KY | 3 | Truck | 2013-08-26 | Jobsite Freer, TX | 2013-09-04 | 9/04: Final Data Book / CD received. 9/03: Expediting Final Data Books. 8/26: Site confirmed receipt. 8/22: Tanks enroute to site. ETA 8/26. 8/16: Material was released to ship today. 8/14: Material was released from inspection today. Waiting on p/l to be submitted before shipment can be made. 8/07: Final inspection now scheduled for 8/14. 7/26: AE inspector to be at shop on 8/02 to check progress. 7/08: Revised Prod. Schedule received. Ship date still Wk of 8/26
G007A | 008364-003-PO-G007A | TD | 0 | 2013-05-14 | LF Manufacturing | Allen Spurger Allen.Spurger@lfm-frp.com 713-979-5428 | TANK Tag: TK-803 | 2013-06-12 | 18-Jun-2013 29-May-2013 21-May-2013 | 20-Jun-2013 10-June-2013 | 2013-06-26 | 2013-07-15 | 2013-07-18 | 22 Jul - 05 Aug 2013 | 2013-07-31 | 2013-07-29 | Giddings, TX | 1 | Truck | 2013-07-30 | Jobsite Freer, TX | 2013-08-05 | 8/5: Final data submitted today electronically, hard copies will be sent this week as well. 7/29: Material was released to ship today. 7/22: Tank was released by the inspector today. Waiting on p/l from vendor before shipment. 7/8: Final inspection set for 18-Jul. 6/24: GA dwg returned to vendor approved. 6/ 18: Vendor submitted the GA dwg today. 6/10: Dwg was returned to vendor AN, fabrication schedule receivd today. 6/4: Waiting on documents to be returned to Vendor, they are still with engieering. 5/29: Calcs and ITP submitted to AE today. 5/22: PO Info sheet and GA dwg received from vendor today. 5/16: Expediting vendor for documents and PO Info Sheet. Vendor needs to nozzle orientations before that GA drwg can be submitted. 5/14: PO issued.
G008 | 008364-003-PO-G008 | TD / LC | 0 | 2013-03-28 | Modern Welding Co. | Kirk Killingsworth 713-675-4211 kkillingsworth@modweldco.com | SUMPS Tag: TK-804, 805, 806 | 09-Jul-2013 13-May-2013 | 16-May-2013 3-May-2013 30-Apr-2013 | 06-Jun-2013 16-May-2013 9-May-2013 | 2013-08-12 | 2013-09-05 | 2013-09-11 | 27 Jun - 25 Jul 2013 | 2013-09-12 | 2013-09-12 | Houston, TX | 1 | Truck | 2013-09-13 | Jobsite Freer, TX | 2013-10-23 | 10/23: Final data book & CD received. 10/14: CO 2 issued to add 1 final data book & CD ro the order. 9/30: AE requesting quote from supplier to provide data book. 9/25: Supplier took exception to final data in quote. Awaiting PM instructions. 9/24: Site confirmed receipt on 9/13. Expediting final data. 9/12: Order released to ship. 9/10: Final inspection delayed to 9/11 due to weather. 9/3: :Leak test occured on the first sump last week, second and third will be completed this week. 8/27: Still on schedule for completion week of 12-Sept. 8/15: Fabrication started this week. 8/6: Fabrication will start next week.
|  |  | 1 | 2013-07-24 |  |  | Change nozzle lengths
|  |  | 2 | 2013-10-14 |  |  | Final Data Book & CD
G009 | 008364-003-PO-G009 | TD | 0 | 2013-04-19 | Pressure Products | Bo Morris 817-249-1338 bo@ppitx.com | VENT STACK Tag: VS-416 | 2013-05-22 | 8-Jul-2013 22-May-2013 30-Apr-2013 | 6-Jun-2013 15-May-2013 | 2013-06-26 | 2013-08-12 | 2013-08-16 | 26 Aug - 23 Sep 2013 | 2013-08-23 | 2013-08-26 | Wheatland, TX | 1 | Truck | 2013-08-27 | Jobsite Freer, TX | 2013-08-28 | 8/27: Material was received at site this week. Final data received. 8/21: Material was released to ship today. 8/15: Final inspection is scheduled for tomorrow. 8/6: Fit up Inspection is Friday Ayg 9, then vessel will be painted. 8/1: On target to start fab in the next week or two. No major issues at this time. 7/23: All material has been received by the vendor. 7/8: Revised GA dwg submitted today. 6/27: Fabrication has started and the inspector visited the shop this week. No major issues to report. 6/20: Vendor is scheduled to start fab middle of next week, inspector has confirmed this info and will be in attendance. 6/12: GA dwgs returned approved and returned last week. 6/5: PO is progressing as scheduled, no major issue or concerns to report.
G011 | 008364-003-PO-G011 | TD / LC | 0 | 2013-04-11 | Schlumberger | Marilyn Boodhai 281-825-2856 mboodhai@slb.com | PIPELINE PUMPS Tag: P-619, 620 | 2013-05-17 | 3-May-2013 22-May-2013 | 15-May-2013 29-May-2013 | 2013-07-08 | 2013-08-23 | 2013-08-30 | 5 - 19 Aug 2013 | 2013-09-06 | 2013-08-29 | Bartlesville, OK | 3 | Truck | 2013-09-03 | Jobsite Freer, TX | 2013-09-25 | 9/26: CD received. 9/25: Final Data received electronically. CD enroute. 9/18: Final data to be sent on 9/25. 9/13: Pumps were shipped without authorization on 8/29 & arrived on site 9/03. 9/09: Pumps released to ship. 9/2: Pumps released by inspector, waiting on packing list before shipment can be released. 8/26: Vendor has improved on the delviery date. Pump will be ready for final inspection this week. 8/20: On schedule for 20-Sept. Date might be improved, vendor to advise. 8/16: last minute wiring change needed to be made. Pushed delviery out to 20-Sep. 8/6: Pumps are to be tested the week of 19-Aug. 8/1: Pumps are being fabricated, no major issues. On track for shipment per the PO. 7/8: Vendor on schedule, all major material received at shop.
G013 | 008364-003-PO-G013 | LC | 0 | 2013-07-30 | R4 Specialities | Danny Ferrara 832-237-6912 danny@r4specialties.com | SPECIALTY ITEMS Tags: See Below |  | 2013-08-08 | 2013-08-19 |  | N/A | N/A | 7 Aug thru 23 Oct 2013 | See Below |  | Houston, TX |  | Truck |  | Jobsite Freer, TX | N/A | 11/06: Strainers received at site. 10/31: Strainers enroute to the site. ETA 11/4. 10/29: Strainers released to ship today to the site. 10/28: R4 advises that strainers scheduled to ship from Sure Flow to site on 10/31 or 11/01. 10/24: Audubon to purchase butterfly valves for duplex strainer. 10/21: R4 working on final solution for strainers. 10/18: R4 still expediting Sure-Flow for delivery improvement. 10/10: R4 reporting problem with Sure-Flow delivery of final strainers. Audubon Procuremnt assisting. 10/08: Expediting R4 for status update on remaining 3 strainers. 9/19: 2nd partial shipment released to ship. 9/17: Exepditing shipment update. 9/10: R4 preparing 2nd shipment. Awaiting P/L. 8/29: 1st partial shipment received at site. 8/27: Partial shipping release issued. 8/20: Expediting status. 8/19: Approval dwgs returned to R4. 8/08: Approval dwgs received at AE. 7/30: PO issued.
[7 empty] | SP-619 | [7 empty] | 2013-10-31 | 2013-10-29 |  | 7
[7 empty] | SP-620 | [7 empty] | 2013-10-31 | 2013-10-29 |  | 7
[7 empty] | SP-103 | [7 empty] | 2013-08-04 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-910 | [7 empty] | 2013-10-31 | 2013-10-29 |  | 7
[7 empty] | SP-141A | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-141B | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-400 | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-804A | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-804B | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-804C | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-804D | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-900 | [7 empty] | 2013-08-07 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-416 | [7 empty] | 2013-08-13 | 2013-08-27 |  | 2 |  | 2013-08-29
[7 empty] | SP-802 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-803 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-415 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-801 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-140 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-607 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-608 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-609 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-610 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-612 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-613 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-614 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-615A | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-615B | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
[7 empty] | SP-617 | [7 empty] | 2013-08-13 | 2013-09-19 |  | 3 |  | 2013-09-23
G013A | 008364-003-PO-G013 | LC | 0 | 2013-10-24 | Sunbelt Supply | Marquita Bacchus - or - Matt Baker 713-672-2222 Marquita.Bacchus@shaleinland.com matthew.baker@sunbeltsupply.com | BUTTERFLY VALVES (4 Each) | N/A | N/A | N/A |  | N/A | N/A | 2013-10-30 | 2013-11-05 | 2013-11-06 | Houston, TX | 1 | Truck | 2013-11-07 | Jobsite Freer, TX | N/A | 11/07: Site confirmed receipt. 11/06: Order shipped to site. ETA 11/07. 10/30: CO 1 issued changing all valves to 1 stem type. Expediting delivery status. 10/19: Supplier to provide only 1 Seat type on BF valves instead of 2. 10/28: Supplier states valves to ship 11/01 or 11/04. 10/24: PO issued with expedited delivery of 1 week.
|  |  | 1 | 2013-10-30 |  |  | Change seat material to UHMWPE on all valves.
I001 | 008364-003-PO-I001 (SO# 7323/7324/7325/7326) | TD | 0 | 2013-04-05 | Accurate Measurement Controls (AMC) | Justin Thibodeaux 337-369-9222 jthibodeaux@accuratemeasurement.net | SENIOR TYPE FITTINGS & METER TUBES Tag: FE-900A Tag: FIT-900A Tag: FE-900B Tag: FIT-900B Tag: FE-454A Tag: FIT-454A Tag: FE-454B Tag: FIT-454B | 7-May-2013 3-June-2013 | 2013-04-30 | 2013-05-14 | 2013-06-11 | 2013-07-01 | 2013-07-10 | 12 - 26 Jul 2013 | 15-Jul-2013 Meters 29-Jul-2013 Thermowells | 2013-07-18 | Broussard, LA | 5 | Truck | 2013-07-19 | Jobsite Freer, TX | 2013-07-29 | 7/29: Final data received was received and approved. 7/23: Material shipped on 18-Jul. 7/16: Meters were released to ship today. 7/8: Four meters will be ready to ship end of this week. Thermowells will ship two weeks later. 6/25: First three units will be hydro tested week of 1-July. 6/19: Vendor is still having issues sourcing the Daniel Fittings but confirms that he has found three other Daniel Fittings that he can use. Waiting on schedule update from vendor. 6/11: Vendor is still trying to improve the one week loss, expediting vendor for updated schedule. 6/3: Vendor is delayed one week. 5/29: Vendor on schedule, no major issues to report. 5/22: Vendor is on schedule for shipment. 5/14: Dwgs returned today to the vendor. 5/7: Schedule received today, ship date is forecast for July 5th.
I002 | 008364-003-PO-I002 (SO# 48CM1) | TD | 0 | 2013-03-28 | Atchafalaya Measurement | Chuck Manuel 337-237-7675 chuck@atchafalayameasurement.com | CORIOLIS METER with TRANSMITTER Tag: FE-910, FIT-910 | N/A | 7-May-13 18-Apr-13 | 2-May-13 | 2013-04-10 | N/A | N/A | 18 Apr - 25 Apr 2013 | 2013-06-14 | 2013-06-20 | Boulder, CO | 5 | Truck | 2013-07-12 | Jobsite Freer, TX | N/A | 6/19: Material was released to ship today. Material will be stored at the vendor for 30-45 days. New forecast ship date is 14-June. 4/29: Material is ready to ship. Need clarification on where to ship material. Jobsite or Sancus. 4/18: Drawings submitted today from vendor. 3/29: Expediting supplier for approval dwgs / docs due to short delivery. 3/28: PO issued.
I003 | 008364-003-PO-I003 | TD / LC | 0 | 2013-04-19 | Puffer Sweiven | Jeremy Carpenter 281-274-1838 Jeremy.Carpenter@puffer.com | CONTROL VALVES | N/A | 2013-05-28 |  | 2013-05-15 | N/A | N/A | 14 Jun & 20 Sep 2013 |  |  | Sherman, TX Marshalltown, IA | 5 | Truck | 17-Sep-2013 10-Sep-2013 11-Jul-2013 | Jobsite Freer, TX | 2013-10-08 | 10/08: Missing documentation received from Puffer. 9/27: PCV-900D received at site. 9/13: PCV-900D shipped to site. ETA 9/17. 9/12: PCV-900D released to ship. 9/09: FCV-601 enroute to site via FedEx freight. ETA 9/10. 9/5: FCV-601 was released to ship today. 8/26: Vendor on schedule for Sept 20th shipment. 8/21: Vendor on schedule for Sept shipment. 8/13: Vendor on schedule for shipment in Sept. 8/6: On schedule for shipment in Sept. 8/1: On schedule for shipment in Sept. 7/15: Last two valves (FCV-601/PCV-900D) are scheduled to ship in Sept. 7/9: PCV-140A was shipped today.
[7 empty] | Tag: FCV-601 | [7 empty] | 2013-09-20 | 2013-09-05
[7 empty] | Tag: LCV-411 | [7 empty] | 2013-06-14 | 2013-06-11
[7 empty] | Tag: LCV-412 | [7 empty] | 2013-06-14 | 2013-06-11
[7 empty] | Tag: LCV-414 | [7 empty] | 2013-06-14 | 2013-06-11
[7 empty] | Tag: LCV-414A | [7 empty] | 2013-06-14 | 2013-06-11
[7 empty] | Tag: LCV-454A | [7 empty] | 2013-06-14 | 2013-06-11
[7 empty] | Tag: LCV-454B | [7 empty] | 2013-06-14 | 2013-06-11
[7 empty] | Tag: PCV-103 | [7 empty] | 2013-06-14 | 2013-06-17
[7 empty] | Tag: PCV-140A | [7 empty] | 2013-06-14 | 2013-07-08
[7 empty] | Tag: PCV-900D | [7 empty] | 2013-09-20 | 2013-09-13
[7 empty] | Tag: PCV-910 | [7 empty] | 2013-06-14 | 17-Jun-13
I003A | 008364-003-PO-I003A | TD / LC | 0 | 2013-04-19 | Puffer Sweiven | Jeremy Carpenter 281-274-1838 Jeremy.Carpenter@puffer.com | CONTROL VALVE Tag: PCV-900C | N/A | 2013-05-30 | 2013-06-10 | 2013-08-01 | N/A | N/A | 2013-09-27 | 2013-09-27 | 2013-09-24 | Stafford, TX | 2 | Truck | 2013-09-25 | Jobsite Freer, TX | 2013-10-24 | 10/24: Missing dwg/docs received. 10/17: Still expediting missing dwg/docs. 10/04: Expediting missing dwg/docs. 9/25: Site confirmed receipt. 9/24: Valve released and shipped to site. 9/17: Vendor still on schedule. 9/5: Vendor on schedule for Sept shipment. 8/27: Vendor on schedule for Sept shipment. 8/21: Vendor on schedule for Sept shipment. 8/14: Vendor on schedule for Sept shipment. 8/8: Vendor on schedule for shipment Sept 27. 8/1: Vendor on schedule, no major issues. 7/15: Vendor on schedule for shipment Sept 27th. 7/10: Vendor on schedule for shipment Sept 27.
I004 | 008364-003-PO-I004 (SO# J-3325) | TD | 0 | 2013-03-28 | Analytical Instruments Corp (AIC) | Gilbert Coody 713-724-5202 gcoody@sbcglobal.net.com | GAS CHROMATOGRAPH with ACCESSORIES Tag: AX-100 | 8-May-13 2-Apr-13 | 2013-04-23 | 2013-04-30 | 2013-04-09 | N/A | 2013-05-30 | 2013-06-20 | 2013-06-11 | 2013-06-12 | Houston, TX | 5 | Truck | 2013-06-17 | Laredo, TX Storage Facility | 2013-07-12 | 7/12: Final data received. 6/19: Material was received in laredo this week. Chasing final vendor documents. 6/12: Vendor shipped material to the Laredo Storage Location. 6/5: vendor on schedule for shipment June 11. 5/22: Vendor is still on schedule. 5/14: FAT scheduled for 30-May, on schedule for ship date of 20-June. 5/8: Prodcution schedule submitted today. 4/30: Dwgs returned approved today 4/24: Expediting vendor dwgs, forecast for sub on 25-Apr. 4/02: Expediting supplier for approval dwgs / docs. Prod. Schedule received with 6/04 Ship date.. 3/28: PO issued.
I005 | 008364-003-PO-I005 | TD | 0 | 2013-04-05 | Puffer Sweiven | Garrett Hargis 281-274-6484 garrett.hargis@puffer.com | LIQUID & GAS FLOW COMPUTER with CABLE Tag: FX-100 | 2013-05-05 | 2013-04-08 | 2013-04-18 | 2013-04-18 | N/A | N/A | 2013-05-25 | 2013-05-24 | 2013-05-28 | Stafford, TX | 1 | Truck | 2013-05-29 | Wilson Dallas, TX | 2013-05-31 | 5/31: Final data received today. 5/29: Computer was shipped to Wilson and received. 5/22: Received ship to adress from Wilson, computer will be shipped once it is ready. 5/7: Weekly update provided today. On schedule for shipment 24-May. 5/1: Vendor is on schedule as of today. Will provide AE weekly updates via email. 4/18: Docs returned to supplier Appoved-For Info Only. 4/08: Received supplier approval docs. 4/05: PO issued.
I006 | 008364-003-PO-I006 | TD | 0 | 2013-05-14 | McJunkin Redman (MRC) | Justin Klein 713-577-3018 Justin.klein@mrcpvf.com | SHUTDOWN VALVES Tag: SDV-415, 454, 601, 900 | 2013-06-06 | 19-Jun-13 22-May-13 | 2013-06-10 | 2013-06-01 | N/A | N/A | 2013-09-20 | 2013-09-03 | 2013-07-10 | Galena Park, TX | 6 | Truck | 2013-07-16 | Jobsite Freer, TX | 2013-04-26 | 7/26: Final vendor data was recieved today. 7/16: Material received at Jobsite. Now waiting on final data from vendor. 7/9: Material is released to ship today. Waiting for receipt from the jobsite. 6/19: Dwgs resubmitted to AE today. 6/10: Vendor schedule received, and dwgs have been returned to vendor. 6/5: Expediting vendor schedule. 5/22: Received the vendor dwgs today. 5/16: Expediting vendor for documents and PO Info Sheet. 5/14: PO issued.
I007 | 008364-003-PO-I007 | TD | 0 | 2013-06-04 | Pentair | Ken Royall 832-261-2510 ken.royall@pentair.com | PRESSURE RELIEF VALVES Tag; PSV-900, 411, 412, 414, 415, 454, 619, 620, 417, 140 | 2013-06-18 | 2013-07-15 | 2013-07-22 | 2013-07-01 | N/A | N/A | 8 - 15 Jul 2013 | 2013-07-26 | 2013-07-30 | Pasedena, TX | 2 | Truck | 2013-07-31 | Jobsite Freer, TX | 2013-08-26 | 8/26: Final data received. 8/5: Waiting for final data to be submitted. 7/30: Material shipped today. 7/24: These are in assembly now. Trying for a Friday shipment. 7/15: Dwgs received today. 7/9: All valves are ready to ship except PSV-412, this PSV will be ready next week. Then order will ship complete. 6/18: Received confirmation from the vendor that order is processed, on track for shipment 10-July. 6/10: Contact is out of the office all week, will return on Monday June 17. 6/04: PO issued.
I008 | 008364-003-PO-I008 | TD | 0 | 2013-05-14 | Puffer Sweiven - Fisher | Jeremy Carpenter Jeremy.Carpenter@puffer.com | PRESSURE REGULATORS Tag: PV-102, 413, 414, 802A, 802B, 800 | 2013-06-18 | 2013-05-30 | 2013-06-10 | 2013-07-01 | N/A | N/A | 24 Jun - 22 Jul 2013 | 30-Jul-2013 PV-102 PV-413 PV-800 PV-414 04-Sep-2013 PV-802A 12-Aug-2013 PV-802B | 30-Jul-2013 PV-102 PV-413 PV-800 PV-414 PV-802A PV-802B | Laredo, TX | 3 | Truck | 2013-08-12 | Jobsite Freer, TX | 2013-09-12 | 9/12: Final Data received. 9/5: Expediting final data. 8/5: Waiting for final data to be submitted. 7/29: Order was ready to ship complete. All items shipped on July 30. 7/15: line item 4 is to upgrade from carbon steel to stainless to shorten lead time. 7/10: Vendor still delayed. Trying to mitigate schedule. 6/18: Ship dates have moved out, no explanation given from vendor. Working to try to mitigate this delay. 6/10: Dwgs were returned today. 6/5: Dwgs are still in review. 5/30: Dwgs received today. 5/22: Waiting on PO info sheet and drwgs 5/16: Expediting vendor for documents and PO Info Sheet. 5/14: PO issued.
I009 | 008364-003-PO-I009 | TD | 0 | 2013-05-14 | Rosemount | Ryan Paulson 800-999-9307 Ryan.paulson@emerson.com | FLOW REGULATORS Tag: FIT-900D, 140, 141, 601 | 2013-05-20 | N/A | N/A | 2013-05-20 | N/A | N/A | 2013-05-28 | 2013-05-28 | 2013-05-30 | Chanhassen, MN | 4 | Truck | 2013-06-04 | Laredo, TX Storage Facility | 2013-06-04 | 6/4: Material was received today. 5/29: Material was released to ship today. Items were shipped to Tito Gonzalez in Laredo, TX. 5/28: PO Info sheet sent, vendor is on schedule for shipment. 5/22: Waiting on PO info sheet. 5/16: Expediting vendor for documents and PO Info Sheet. 5/14: PO issued.
I010 | 008364-003-PO-I010 | TD | 0 | 2013-05-14 | Rosemount | Ryan Paulson 800-999-9307 Ryan.paulson@emerson.com | PRESSURE TRANSMITTERS Tag: PIT-900, 900A, 900C, 901, 412, 140A, 454A, 454B, 910, 601, 601A, 414, 103, 102, PDIT-454A | 2013-05-23 | N/A | N/A | 2013-05-28 | N/A | N/A | 2013-06-03 | 2013-06-03 | 2013-06-05 | Chanhassen, MN | 5 | Truck | 2013-06-10 | Laredo, TX Storage Facility | 2013-06-06 | 6/10: Final documents were received today. Waiting confirmation of shipment receipt from Laredo. 6/5: Material was released to ship today. Items were shipped to Tito Gonzalez in Laredo, TX. 5/28: PO Info sheet sent, vendor is on schedule for shipment. 5/22: Waiting on PO info sheet. 5/16: Expediting vendor for documents and PO Info Sheet. 5/14: PO issued.
I011 | 008364-003-PO-I011 | TD | 0 | 2013-05-14 | Rosemount | Ryan Paulson 800-999-9307 Ryan.paulson@emerson.com | TEMP. TRANSMITTERS Tag: TIT-454, 100 | 23-May-2013 5-Jun-2013 | Final Data Only | Final Data Only | 2013-06-03 | N/A | N/A | 2013-06-24 | 2013-06-19 | 2013-06-20 | Chanhassen, MN | 5 | Truck | 2013-06-25 | Laredo, TX Storage Facility | 2013-07-09 | 7/09: final docs received today. 6/24: Waiting on confirmation of receipt. 6/19: Material was released to ship today. Will be shipped to Laredo. 6/5: Received update today, vendor is on schedule per the PO ship date. 5/28: PO Info sheet sent, vendor is on schedule for shipment. 5/22: Waiting on PO info sheet. 5/16: Expediting vendor for documents and PO Info Sheet. 5/14: PO issued.
I012 | 008364-003-PO-I012 | TD | 0 | 2013-07-22 | Rosemount | Ryan Paulson 800-999-9307 Ryan.paulson@emerson.com | Level Transmitters LIT-414A LIT-801 LIT-804 LIT-805 LIT-806 LIT-900 |  | Final Data Only | Final Data Only | 2013-07-30 | N/A | N/A | 2013-08-12 | 2013-08-08 | 2013-08-12 | Chanhassen, MN | 5 | Truck | 2013-08-16 | Jobsite Freer, TX | 2013-08-20 | 8/20: Final docs received today. 8/16: Maaterial was received today. 8/12: material was released to ship today. 8/1: Vendor is on schedule for shipment the week of the 8th. 22-Jul: PO was awarded today.
I013 | 008364-003-PO-I013 | LC | 0 | 2013-07-23 | Chase Controls | Dan Edwards 281-397-7099 dedwards@chasecontrols.com | GAUGES & SWITCHES LG-411/412/413/414/414A/ 415/416/ 454A/454B LS-416/LSH-416/LSHH-900/LSLL-900/LG-900A/B/C |  | 26-Aug-2013 31-Jul-2013 | 28-Aug-2013 22-Aug-2013 14-Aug-2013 |  | N/A | N/A | 26 Aug - 2 Sep-13 | Wk of 9 Sep | 2013-09-11 | Houston, TX | 5 | Truck | 2013-09-17 | Jobsite Freer, TX | 2013-10-04 | 10/09: Final data books received 10/04. 10/08: Expediting final data books. 9/24: Site confirms receipt on 9/17. 9/11: Order shipped. ETA 9/13 9/10: order released to ship. 9/05: Order scheduled for shipment the wk of 9/09. Awaiting P/L. 8/28: Missing dwgs returned to Chase Approved. 8/26: Missing dwgs received at Audubon. 8/21: Expediting missing approval dwgs for LG-414A & 416. 8/14: Approval dwgs returned. 7/31: Approval Dwgs / Docs received.
I014 | 008364-003-PO-I014 | LC | 0 | 2013-06-06 | R4 Specialities | Danny Ferrara 832-237-6912 danny@r4specialties.com | ROTAMETER Tag: FI-413 |  | 2013-06-07 | 2013-07-03 |  | N/A | N/A | 2013-08-08 | 2013-07-22 | 2013-07-18 | Houston, TX | 2 | Truck | 2013-07-23 | Jobsite Freer, TX | N/A | 7/26: Shipped on 7/18. Delivered 7/23. Receipt confirmed. 7/18: Released to ship. Awaiting shipping details. 7/12: Expediting status update. 7/03: Dwgs / Docs Approved. 6/21: Expediting approval dwgs / docs. 6/07: Dwgs / Docs for approval received.
I015 | 008364-003-PO-I015 | LC | 1 | 2013-05-14 | R4 Specialities | Danny Ferrara 832-237-6912 danny@r4specialties.com | PRESSURE & TEMP. GAUGES Tag: PI-900, 900A, 140A, 141A, 454B, 103A, 619, 620, 608, 612, 609, 413, 413A, 615A, 615B, 802, 803, 613, 614, 610, 140B, 140C, 140D, 140, 141, 800, 802A, 802B, 102, 417, 407C, 910, 619, 620, 802, 803, 411, TW-802, TW-803,TW-411, |  | 22-Jul-2013 3-Jul-2013 | 24-Jul-2013 19-Jul-2013 |  | N/A | N/A | 24 Jun - 1 Jul 2013 | 2013-07-30 | 2013-07-16 | Houston, TX | 2 | Truck | 2013-07-23 | Jobsite Freer, TX | N/A | 7/25: Receipt confirmed. 7/16: Order shipped to site. ETA 7/18. 7/09: TW's must be replaced with new ones due to engineering error. Order delayed 2-3 weeks. 7/03: Calibration Certs received for approval. 6/25: Order to be ready to ship early Jul pending approval of calibration certs. 6/21: Expediting supplier for order status. 6/07: CO 1 issued to revise Tag PI-802B. 5/28: Supplier will provide Calibration Certs after receipt at his location. No other docs are required. 5/22: Vendor on schedule, but need approval dwgs to be submitted.
I017 | 008364-003-PO-I017 | TD | 0 | 2013-05-16 | Wilson Instruments | Kelvin Thornton 361-772-4765 Kelvin.thornton@wilson-instuments.com | PLC CONTROL SYSTEM Tag: N/A | 2013-06-01 | Submitted AS | N/A | 2013-06-01 | N/A | 2013-11-15 | JB/MCP 24-Jul-2013 01-Dec-2013 | 24-Jul-2013 JB/MCP 22-Nov-2013 |  | Carthage, TX |  | Truck | 2013-12-03 | Jobsite Freer, TX |  | 1/21: Expediting final data books. 1/09: Received site confirmation of final shipment of all items. 12/19: Wilson states all items shipped to site. Awaiting copies of shipping docs. 12/17: Expediting status. 12/05: Currerntly in I/O checkout. Supplier to advise ship date. 11/29: Expediting status of remianing items. 10/29: Revised RIO panel dwgs received at Audubon. 10/17: RIO Panel Redlines sent to Wilson. 9/11: Wilson personnel at MCSI for pre-FAT on MCC Bldg. 9/6: No major issues currently. 8/26: Still on schedule for software FAT in Nov. 8/12: Software FAT will be mid November. 8/5: JBs have arrived on site Jul 26 and the MCP has arrived at MCSI.
I020 | 008364-003-PO-I020 | LC | 0 | 2013-05-14 | R4 Specialities | Danny Ferrara 832-237-6912 danny@r4specialties.com | ORIFICE PLATES Tag: FE-900D Tag: FE-140 Tag: FE-141 Tag: FE-601 | [6 empty] | 2013-08-01 | 2013-06-30 | 2013-06-12 | Houston, TX | 1 | Truck | 2013-06-13 | Laredo, TX Storage Facility | N/A | 6/20: Receipt confirmed. 6/11: Order released to ship. 6/10: Dwgs approved. 5/28: Dwgs received. 5/16: PO issued.
I021 | 008364-003-PO-I021 | LC | 0 | 2013-06-05 | R4 Specialities | Danny Ferrara 832-237-6912 danny@r4specialties.com | LEVEL SWITCHES Tag: LSH-806A Tag: LSH-805A Tag: LSH-804A |  | 2013-06-13 | 2013-06-25 |  |  |  | 2013-08-15 | 2013-08-09 | 2013-08-12 | Houston, TX | 1 | Truck | 2013-08-13 | Jobsite Freer, TX | N/A | 8/13: Site receipt confirmed. 8/12: Shipped to site. 8/08: Switches in-house at R4. Released to ship. 8/02: R4 says switches will be ready to ship on 8/16. 7/26: Re-checking delivery status. 7/12: Supplier reports order still on schedule for 8/15 shipment. 6/25: Cut-sheets Approved for Information.
INSERT NEW ROWS ABOVE THIS LINE!
(Company Address)
(Company Registration No.)